## Tasks
| phases | october | [6 empty] | november | [6 empty] | december | [6 empty] | january |  |  |  | february |  |  |  | march |  |  |  | april
|  | week 1 |  |  | week 2 | week 3 |  | week 4 | week 5 | week 6 | week 7 |  | week 8 |  |  | week 9 | week 10 |  |  | week 11 |  | week 12 | week 13 | week 14 | week 15 | week 16 | week 17 | week 18 | week 19 | week 20 | week 21 | week 22 | week 23 | week 24 | week 25 | week 26 | week 27 | week 28
| Planning and Design | Introduction (3 days)
[6 empty] | Requirements 15–22 Oct | [5 empty] | ERD 20-30 nov
Aims & obj. (4 days)
[7 empty] | Project Planning 22–31 Oct |  |  |  | risk register 15–22 nov |  |  | Test Plan 25 nov-7 dec
Literature Review (14 days)
[9 empty] | UML Design 1–14 nov | [5 empty] | Normalization 25 nov-8 dec
Setup implementation
Helper Func. 10-19 dec
Authentication 19-25 dec
Tkinter UI 9-15 dec
database 15-21 dec
Main implementation
Introduction (3 days) by Ava