## Project schedule
| Systems Development Group Project | [7 empty] | Project start: | [7 empty] | 2025-10-01
| Paragon Apartment Management System | [7 empty] | Display week: | [7 empty] | 1
| UFCF7S-30-2 |  | Project Members: Mohamed, Ava, Leyla, Erin, Chiko
[9 empty] | 2025-10-01 | [13 empty] | Oct 13, 2025 | [13 empty] | Oct 27, 2025 | [13 empty] | Nov 10, 2025 | [13 empty] | Nov 24, 2025 | [13 empty] | Dec 8, 2025 | [13 empty] | Dec 22, 2025 | [13 empty] | Jan 5, 2026 | [13 empty] | Jan 19, 2026 | [13 empty] | Feb 2, 2026 | [13 empty] | Feb 16, 2026 | [13 empty] | Mar 2, 2026 | [13 empty] | Mar 16, 2026
ID | TASK | DEPENDENCIES | ASSIGNED TO | PROGRESS | START | END | SKILL NEEDED | time axis 2025-09-29 to 2026-03-29
 | time axis 2025-09-29 to 2026-03-29
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning and Design
A1 | Aims & Objectives | NONE | All Group Members | 100% | 2025-10-01 | 2025-10-08 | Goal setting, Documentation, Research, Teamwork | 8
A2 | Literature Review | A1 | Leyla & Ava & Mohamed | 100% | 2025-10-08 | 2025-10-14 | Research, Documentation | 7
A3 | Create Schedule & Gantt Chart | A1 | Mohamed & Ava | 100% | 2025-10-14 | 2025-10-20 | Scheduling, Documentation, Communication | 7
A4 | Requirements Analysis | A1 | Mohamed, Ava, Leyla, Erin | 100% | 2025-10-20 | 2025-10-27 | Documentation, Research, Team-work | 8
System Design
B1 | Class diagram | A4 | Ava | 100% | 2025-10-27 | 2025-11-26 | UML, System Modelling | 31
B2 | Use case Diagram | A4 | Erin | 100% | 2025-10-27 | 2025-12-01 | UML, OOP, System Modelling | 36
B3 | Sequence Diagrams | A4 | Mohamed | 100% | 2025-11-09 | 2025-12-19 | UML, Flow Design | 41
D1 | ERD Design | A4 | Leyla & Ava | 100% | 2025-11-26 | 2025-12-06 | Database Modelling, SQL
C1 | Risk Register | A4 | Erin | 100% | 2025-12-29 | 2026-01-18 | Risk Analysis, Documentation | 21
Execution
E1 | UI & Helper Components | A1, B1, D1 | Chiko, Mohamed | 100% | 2025-11-26 | 2025-12-26 | Tkinter, Python, UI Components | 31
E2 | Dashboard Template | A1, B1, D1 | Chiko | 100% | 2025-12-19 | 2026-01-18 | UI Design, Layout, Components | 31
D1 | Database Normalisation | B1, B2, D1 | Leyla & Ava | 100% | 2025-12-19 | 2026-01-02 | SQL, Table Design, Queries | 15
D2 | Database Implementation | B1, B2, D1 | Chiko & Mohamed | 100% | 2026-01-23 | 2026-02-02 | SQL, Table Design, Queries | 11
F1 | Authentication System | B1, B2 | Mohamed | 100% | 2026-01-28 | 2026-02-17 | Security, Login, RBAC | bar: 2026-01-28 to 2026-02-17
G1 | Admin Module - Core | E1, B1 | Mohamed & Chiko | 100% | 2025-12-19 | 2026-01-08 | Backend, CRUD, Role Management | 21
G2 | Admin - Finance & Security | E1, B1 | Mohamed & Chiko | 100% | 2025-12-19 | 2025-12-26 | Finance, Security, Reporting
G3 | Manager - Operations | E2, D1 | Mohammed | 100% | 2025-12-24 | 2026-01-08 | Operations, Approval, Backend
G4 | Manager - Reports | E2, D1 | Chiko | 100% | 2025-12-28 | 2026-01-06 | Analytics, Reporting, SQL
G5 | Finance - Transactions & Reports | E1, F1, D2 | Chiko, Mohammed | 100% | 2026-01-02 | 2026-01-18 | Payment Processing, Backend
G6 | Maintenance - Requests | E1, B1 | Mohammed | 100% | 2026-01-18 | 2026-01-28 | Reporting, Billing, SQL
G7 | Maintenance - Scheduling | E1, E2, D2 | Mohammed | 100% | 2026-01-20 | 2026-01-30 | Maintenance Tracking, Logging
G8 | Front desk - Registration | E1, E2, D2 | Ava, Leyla, Erin | 100% | 2026-02-09 | 2026-02-23 | Scheduling, Notifications
G9 | Front Desk - Records | E1, E2, D3 | Ava, Leyla, Erin | 100% | 2026-02-09 | 2026-02-25 | Registration, Data Entry
G10 | Tenant - Profile | E1, E2, D4 | Erin,chiko | 100% | 2026-02-23 | 2026-03-09 | Record Updates, Logging
G11 | User management | D1, E1, E2 | Ava | 100% | 2026-03-01 | 2026-03-08 | User data, Privacy Handling, UI, Access Control
G12 | Lease management | D1, E1, E3 | Leyla | 100% | 2026-02-27 | 2026-03-07 | Lease Data, Privacy, Access Control, UI
H1 | Security & Validation | All | All Group Members | 100% | 2026-03-12 | 2026-03-19 | Authentication, SQL, Audit
Evaluation & Reporting
I1 | Monitor progress | None | All Group Members | 100% | 2025-10-01 | 2026-03-30 | Testing, Verification, Comminication, Team-working | 181 | bar: 2025-10-01 to 2026-02-28
I2 | Formative Peer Review | None | All Group Members | 100% | 2025-10-01 | 2026-03-30 | Communication, Teamwork | 181
I3 | Final Testing and testing plan | All | Mohamed,chiko,and leyla | 100% | 2025-10-01 | 2026-03-30 | Validation, Documentation, Communication | Report Writing, Documentation, Referencing, Communication
I4 | Compile Final Report | All | All Group Members | 100% | 2026-03-19 | 2026-03-30 | Report Writing, Documentation, Referencing, Communication | 12
I5 | Individual Reflection & Demo | All | All Group Members | 100% | 2026-03-19 | 2026-03-30 | Reflection, Presentation | 12