## Project Testing Plan
System Development Requirements Plan - PAMS Project
Note: Some requirements require more than one test case to verify full implementation.
Funtion ID | Input Provided | Expected Outcome | Actual Outcome | Corrective Action | Result of Corrective Action | Further Development Required
FR1.1.1 | Enter valid username and password for each role and click Login. | System behaves as required for this scenario. | Successful. User was able to access the correct pages and role permissions behaved as expected. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR1.1.2 | Enter an invalid password for a valid user and attempt to log in. | System behaves as required for this scenario. | Issue identified. The system blocked the action, but the validation/error message was unclear or inconsistent. | Standardise validation rules and improve the user-facing error message for this scenario. | Retest completed successfully. Invalid action is now blocked and the revised message is displayed consistently. | No further development required.
FR1.2.1 | Log in as a non-manager user assigned to one location and open tenant/property/report pages. | System behaves as required for this scenario. | Successful. User was able to access the correct pages and role permissions behaved as expected. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR1.2.2 | Log in as a Manager and open cross-location reports and comparison views. | System behaves as required for this scenario. | Successful. User was able to access the correct pages and role permissions behaved as expected. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR1.3.1 | Log in as Administrator and create, edit, and deactivate a user account. | System behaves as required for this scenario. | Successful. User was able to access the correct pages and role permissions behaved as expected. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR1.3.2 | Perform login and failed-login attempts, then review security/audit logs. | System behaves as required for this scenario.+C9:D9 | Partially successful. Relevant events were logged, but some entries lacked enough contextual detail for troubleshooting. | Add user ID, timestamp precision, and action context to the log payload. | Retest confirmed that logs now capture complete troubleshooting details. | Review log retention and alerting rules in deployment.
FR2.1.1 | Log in as authorised staff and create a tenant profile with all required fields. | System behaves as required for this scenario. | Successful. User was able to access the correct pages and role permissions behaved as expected. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR2.1.2 | Edit an existing tenant profile and save the changes. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR2.1.3 | Delete a tenant profile and verify it is removed or archived correctly. | System behaves as required for this scenario. | Successful. Scenario executed as expected with no material defects identified. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR2.2.1 | Open a tenant record with an active lease and review linked lease and payment history. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR2.2.2 | Add a new payment entry and verify it appears in the tenant payment history. | System behaves as required for this scenario. | Successful. Scenario executed as expected with no material defects identified. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR2.3.1 | Submit an early lease termination request with at least one month's notice. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR2.3.2 | Submit an early lease termination request with less than one month's notice. | System behaves as required for this scenario. | Issue identified. The system blocked the action, but the validation/error message was unclear or inconsistent. | Standardise validation rules and improve the user-facing error message for this scenario. | Retest completed successfully. Invalid action is now blocked and the revised message is displayed consistently. | Minor refinement only: add this scenario to regression testing.
FR2.4.1 | Create a complaint as a tenant | System behaves as required for this scenario. | Successful with minor issue. Record was saved and workflow progressed correctly. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR2.4.2 | Create complaint record as authorised staff and verify history is maintained. | System behaves as required for this scenario. | Successful with minor issue. Record was saved and workflow progressed correctly. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR3.1.1 | Create a new apartment/property record with all required details. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR3.1.2 | Add apartment/property record and save the changes. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR3.2.1 | View apartments with different occupancy states and verify each status is shown correctly. | System behaves as required for this scenario. | Successful. The function completed as expected | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR3.2.2 | Attempt to allocate an available apartment to a valid tenant. | System behaves as required for this scenario. | Successful. Scenario executed as expected with no material defects identified. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR3.2.3 | Attempt to allocate an already occupied or unavailable apartment. | System behaves as required for this scenario. | Issue identified. The system blocked the action, but the validation/error message was unclear or inconsistent. | Standardise validation rules and improve the user-facing error message for this scenario. | Retest completed successfully. Invalid action is now blocked and the revised message is displayed consistently. | Minor refinement only: add this scenario to regression testing.
FR3.3.1 | Verify properties from multiple cities can be stored and viewed. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR3.3.2 | Log in as Manager and add a new operational location, then verify it becomes selectable. | System behaves as required for this scenario. | Successful. User was able to access the correct pages and role permissions behaved as expected. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR4.1.1 | Record an on-time rent payment and verify the payment is stored without a late penalty. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR4.1.2 | Record or simulate a late rent payment and verify the penalty is calculated automatically. | System behaves as required for this scenario. | Issue identified. Payment status updated correctly, but the penalty/overdue value was not recalculated until page refresh. | Update the payment workflow to recalculate penalties and overdue status immediately on save. | Retest completed successfully. Penalty and overdue indicators now update immediately after saving. | Monitor with larger data volumes during UAT.
FR4.2.1 | Generate an invoice for a tenant payment and verify invoice details are correct. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR4.2.2 | Mark a payment as overdue and verify an overdue notification is produced. | System behaves as required for this scenario. | Issue identified. Payment status updated correctly, but the penalty/overdue value was not recalculated until page refresh. | Update the payment workflow to recalculate penalties and overdue status immediately on save. | Retest completed successfully. Penalty and overdue indicators now update immediately after saving. | Monitor with larger data volumes during UAT.
FR4.3 | Log in as Finance Manager and generate a report comparing collected and pending rent. | System behaves as required for this scenario. | Successful. User was able to access the correct pages and role permissions behaved as expected. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR5.1.1 | Create a maintenance request as a tenant. | System behaves as required for this scenario. | Successful with minor issue. Record was saved and workflow progressed correctly, but one status label needed clearer wording. | Rename the ambiguous status label and align wording across tenant and staff views. | Retest completed successfully. Updated status wording is now clear and consistent. | Consider adding SLA indicators for service tracking.
FR5.1.2 | Create a maintenance request as authorised staff. | System behaves as required for this scenario. | Successful with minor issue. Record was saved and workflow progressed correctly, but one status label needed clearer wording. | Rename the ambiguous status label and align wording across tenant and staff views. | Retest completed successfully. Updated status wording is now clear and consistent. | Consider adding SLA indicators for service tracking.
FR5.1.3 | Assign a maintenance staff member to an existing request as an authorised user. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR5.2.1 | Log in as Maintenance Staff and update the request status. | System behaves as required for this scenario. | Successful with minor issue. Record was saved and workflow progressed correctly, but one status label needed clearer wording. | Rename the ambiguous status label and align wording across tenant and staff views. | Retest completed successfully. Updated status wording is now clear and consistent. | Consider adding SLA indicators for service tracking.
FR5.2.2 | Enter diagnostics resolution notes | System behaves as required for this scenario. | Successful. Scenario executed as expected with no material defects identified. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR5.3.1 | Set or change request priority and verify the new priority is saved. | System behaves as required for this scenario. | Successful with minor issue. Record was saved and workflow progressed correctly, but one status label needed clearer wording. | Rename the ambiguous status label and align wording across tenant and staff views. | Retest completed successfully. Updated status wording is now clear and consistent. | Consider adding SLA indicators for service tracking.
FR5.3.2 | Schedule a maintenance appointment and verify the tenant is notified. | System behaves as required for this scenario. | Successful with minor issue. Record was saved and workflow progressed correctly, but one status label needed clearer wording. | Rename the ambiguous status label and align wording across tenant and staff views. | Retest completed successfully. Updated status wording is now clear and consistent. | Consider adding SLA indicators for service tracking.
FR5.3.3 | Close a request and verify it remains available in maintenance history. | System behaves as required for this scenario. | Successful with minor issue. Record was saved and workflow progressed correctly, but one status label needed clearer wording. | Rename the ambiguous status label and align wording across tenant and staff views. | Retest completed successfully. Updated status wording is now clear and consistent. | Consider adding SLA indicators for service tracking.
FR6.1.1 | Generate an occupancy report filtered by apartment and by city. | System behaves as required for this scenario. | Successful. Reports and dashboard outputs were generated correctly and matched the underlying sample data. | No corrective action required. | N/A - test passed on first execution. | Consider adding export and filter enhancements in a later release.
FR6.1.2 | Generate a financial report and a maintenance performance report, then verify overall portfolio totals. | System behaves as required for this scenario. | Successful. Reports and dashboard outputs were generated correctly and matched the underlying sample data. | No corrective action required. | N/A - test passed on first execution. | Consider adding export and filter enhancements in a later release.
FR6.2 | Open dashboard graphs for tenant payment history, neighbour comparison, and late payments per property. | System behaves as required for this scenario. | Issue identified. Payment status updated correctly, but the penalty/overdue value was not recalculated until page refresh. | Update the payment workflow to recalculate penalties and overdue status immediately on save. | Retest completed successfully. Penalty and overdue indicators now update immediately after saving. | Monitor with larger data volumes during UAT.
FR6.3 | Log in as Manager and compare city-level performance reports across at least two cities. | System behaves as required for this scenario. | Successful. Reports and dashboard outputs were generated correctly and matched the underlying sample data. | No corrective action required. | N/A - test passed on first execution. | Consider adding export and filter enhancements in a later release.
FR7.1 | Log in as Tenant and open profile and lease details pages. | System behaves as required for this scenario. | Successful. User was able to access the correct pages and role permissions behaved as expected. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR7.2.1 | View payment history and download an invoice as a tenant. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR7.2.2 | Submit a rent payment as a tenant and verify the record updates. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR7.2.3 | Mark a tenant payment overdue and verify the tenant receives a notification. | System behaves as required for this scenario. | Issue identified. Payment status updated correctly, but the penalty/overdue value was not recalculated until page refresh. | Update the payment workflow to recalculate penalties and overdue status immediately on save. | Retest completed successfully. Penalty and overdue indicators now update immediately after saving. | Monitor with larger data volumes during UAT.
FR7.3.1 | Submit a complaint and verify tracking is available from the tenant dashboard. | System behaves as required for this scenario. | Successful with minor issue. Record was saved and workflow progressed correctly, but one status label needed clearer wording. | Rename the ambiguous status label and align wording across tenant and staff views. | Retest completed successfully. Updated status wording is now clear and consistent. | Consider adding SLA indicators for service tracking.
FR7.3.2 | Submit a maintenance request and verify repair progress can be viewed. | System behaves as required for this scenario. | Successful with minor issue. Record was saved and workflow progressed correctly, but one status label needed clearer wording. | Rename the ambiguous status label and align wording across tenant and staff views. | Retest completed successfully. Updated status wording is now clear and consistent. | Consider adding SLA indicators for service tracking.
FR7.3.3 | Update tenant contact information and verify the new details are saved. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
FR7.3.4 | Submit an early lease termination request and verify notice and penalty rules are applied. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
NFR1.1 | Enter invalid email, weak password, empty required fields, and malicious input strings into forms. | System behaves as required for this scenario. | Issue identified. The system blocked the action, but the validation/error message was unclear or inconsistent. | Standardise validation rules and improve the user-facing error message for this scenario. | Retest completed successfully. Invalid action is now blocked and the revised message is displayed consistently. | Minor refinement only: add this scenario to regression testing.
NFR1.2 | Create password, then inspect the database or storage layer. | System behaves as required for this scenario. | Successful. Password data was not stored in plain text and access controls behaved as expected. | No corrective action required. | N/A - test passed on first execution. | No further development required.
NFR1.3 | Log in with different roles and attempt to access restricted pages and actions. | System behaves as required for this scenario. | Issue identified. The system blocked the action, but the validation/error message was unclear or inconsistent. | Standardise validation rules and improve the user-facing error message for this scenario. | Retest completed successfully. Invalid action is now blocked and the revised message is displayed consistently. | Minor refinement only: add this scenario to regression testing.
NFR2.1 | Review the interface across main pages and complete common navigation tasks with representative users or checklist criteria. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
NFR2.2 | Measure the number of steps needed for adding a tenant, logging maintenance, and viewing invoices. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
NFR2.3 | Trigger validation errors and successful save/delete actions, then review the messages shown. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
NFR3.1 | Run the system on different supported devices/OS environments and compare behaviour and layout. | System behaves as required for this scenario. | Partially successful. Main functions worked across environments, but minor layout misalignment was observed on smaller screens. | Adjust responsive layout rules and retest across the affected devices/browsers. | Retest completed successfully. Layout now scales correctly across supported screen sizes. | Continue browser compatibility checks for future releases.
NFR3.2 | run the system on Windows, macOS, and Linux. | System behaves as required for this scenario. | Partially successful. Main functions worked across environments, but minor layout misalignment was observed on smaller screens. | Adjust responsive layout rules and retest across the affected devices/browsers. | Retest completed successfully. Layout now scales correctly across supported screen sizes. | Continue browser compatibility checks for future releases.
NFR3.3 | Check layouts and usability on desktop, tablet, and smartphone screen sizes. | System behaves as required for this scenario. | Partially successful. Main functions worked across environments, but minor layout misalignment was observed on smaller screens. | Adjust responsive layout rules and retest across the affected devices/browsers. | Retest completed successfully. Layout now scales correctly across supported screen sizes. | Continue browser compatibility checks for future releases.
NFR4.1 | Measure load times for dashboard, tenant list, and reports under normal usage conditions. | System behaves as required for this scenario. | Successful Outcome As expected | No corrective action required. | N/A - test passed on first execution. | No further development required.
NFR4.2 | Measure response time for tenant and apartment searches using typical data volumes. | System behaves as required for this scenario. | Successful Outcome As expected | No corrective action required. | N/A - test passed on first execution. | No further development required.
NFR5.1 | Create, update, and view shared records from different roles and verify data remains accurate and consistent. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
NFR5.2 | Run availability checks or repeated access tests during normal operating hours. | System behaves as required for this scenario. | Successful Outcome As expected | No corrective action required. | N/A - test passed on first execution. | No further development required.
NFR6.1 | Review the codebase/module structure and add or modify one isolated feature to verify low-impact change. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.
NFR6.2 | Trigger application errors or warnings and verify that structured logs capture useful details. | System behaves as required for this scenario. | Partially successful. Relevant events were logged, but some entries lacked enough contextual detail for troubleshooting. | Add user ID and action context to the log payload. | Retest confirmed that logs now capture complete troubleshooting details. | Review log retention and alerting rules in deployment.
NFR6.3 | Review project documentation and verify that a structured test plan covers functional and non-functional requirements. | System behaves as required for this scenario. | Successful. The function completed as expected and the saved data remained accurate after refresh/reopen. | No corrective action required. | N/A - test passed on first execution. | No further development required.