## Risk Register
Table 1: Full Risk Register
ID | Risk Description | Root Cause | Triggers | Consequences | Frequency | Severity | Weight | Overall Rating | Weighted Score | Catagory | Mitigation | Priority | Response | Responsible
R1 | Bugs and errors in the system | Complext codebase with several components | Features failing shown by error messages during training | Delays in timeline with a temporary reduction in system reliability and increased work/tasks | 4 | 3 | 3 | 12 | 36 | Technical | Conduct regular testing for unexpected behaviour | Medium | Debug system and test new stable version | Tester
R2 | Schedule delays | Underestimated task durations | Tasks being uncompleted by deadline | Missed milestones and rushed work | 3 | 4 | 3 | 12 | 36 | Project Management | Regular progress checks | Medium | Reallocate tasks and adjust Gahntt chart | Whole Team
R3 | Failure to follow GDPR requirments | Insufficient understanding/research of data protection laws | Missing consent and unclear data sources | Legal breaches, project failure and reputational damage | 2 | 5 | 4 | 10 | 40 | Legal | Use annonymus data in testing, team awareness of GDPR guildlines and restriction to sensitive data | High | Immediate removal of any non-complient data, update data handling procedures and team training | Whole Team
R4 | Project expanding passed agreed requirments with extra features/increased functionality | Lack of clearly defined scope boundaries, team enthusiasm leading to unnecessary additions | Work being completed not listed in the plan | Increased workload, delays and missed deadlines | 3 | 4 | 3 | 12 | 36 | Project Management | Regular comparissons of work to agreed scope as well as a functional proccess for approving changes | Medium | Stop work on unapproved features, re-prioratise tasks to return to agreed scope | Project Lead
R5 | System incompatability across operating systems | System not designed, built or tested across multiple operating systems | System fails to run/ displays errors on a different OS | Support issues for users unable to access the system | 3 | 2 | 2 | 6 | 12 | Technical | Cross platform testing and avoid OS-specific dependancies | Low | Fix OS-specific issues immedietly | Whole Team
R6 | Unclear requirements | Ambitious case study with complex requirments and multiple components to track | Repeated clarification questions and confusion within the team | Incorrect features and delays | 4 | 4 | 4 | 16 | 64 | Project Management | Requirment clarification meetings | High | Re-evaluate tasks and update requirment list | Project Lead
R7 | Poor communication | No structured communication | Missed meetings/unanswered messages | Misaligned work and possible duplicated components | 2 | 4 | 3 | 8 | 24 | Operational | Set fixed weekly meetings and make use of shared channel (discord etc) | Low | Reinforce communication schedule | Whole Team
R8 | Integration issues with modules | Components developed independently | Merge conflicts and incompatibility with components | System instability and delays | 4 | 3 | 3 | 12 | 36 | Technical | Integrate frequently, utalise github branching as well as communicating structure of modules with team | Medium | Reasses code and implement immediate integration testing | Developer
R9 | Accidental deletion or corruption of files | No automatic backups | Accidental deletion or system crash | Loss of progress and delays in schedule | 3 | 4 | 3 | 12 | 36 | Technical | Enable regular backups and version control | Medium | Restore from backup and review/improve handling process | Whole Team
R10 | University case study updates affecting project requirements | Stakeholders' redefining requirments mid project | New documents or instructions released | Timeline disruption and requirment confusion | 1 | 5 | 2 | 5 | 10 | Project Management | Monitor announcments closely | Low | Reassess completed work and adjust timeline for planning | Project Lead
R11 | Team member unable to complete task in time eg illness | Lack of contingency planning and sickness management | Member of team unavailable for period of time | Increased workload on remaining team members, missed deadlines | 3 | 3 | 2 | 9 | 18 | Operational | Have team members ready and willing to cover redistribution of tasks equally | Low | Reasign tasks and temporarily adjust ghant chart | Whole Team
R12 | Data breaches (SQL injection attacks, unauthorised action etc) | Weak access control, lack of data loss prevention and insufficient security awareness | Suspicious login attempts and access errors | Severe legal issues and reputational damage | 2 | 5 | 4 | 10 | 40 | Technical | Strong technical security controls within python code and SQL database eg paramatizes queries, secure database permissions etc | High | Revoke access and investigate breach to restore a secure system version | Whole Team

## Scoring System
Table 2: Scoring
Number Value | Severity | Frequency
1 | Insignificant | Rare
2 | Minor | Unlikely
3 | Moderate | Possible
4 | Major | Likely
5 | Severe | Very Likely
Table 3: Weighted Importance
Number Value | Weighted Importance
1 | Low
2 | Moderate
3 | High
4 | Critical

## Catagory Analysis
Table 4: Category Frequency Counts
Category | F1 | F2 | F3 | F4 | F5 | Total Risks | Frequency Weighted Avg
Technical | 0 | 1 | 2 | 2 | 0 | 5 | 3.2
Project Management | 1 | 0 | 2 | 1 | 0 | 4 | 2.75
Operational | 0 | 1 | 1 | 0 | 0 | 2 | 2.5
Legal | 0 | 1 | 0 | 0 | 0 | 1 | 2
Table 5: Severity Counts
Category | S1 | S2 | S3 | S4 | S5 | Total Risks | Severity Weighted Avg
Technical | 0 | 1 | 2 | 1 | 1 | 5 | 3.4
Project Management | 0 | 0 | 0 | 3 | 1 | 4 | 4.25
Operational | 0 | 0 | 1 | 1 | 0 | 2 | 3.5
Legal | 0 | 0 | 0 | 0 | 1 | 1 | 5
Table 6: Final Category Rating
Catagory | Final Rating | Rank (1 = Most Critical)
Technical | 10.88 | 2
Project Management | 11.6875 | 1
Operational | 8.75 | 4
Legal | 10 | 3