## Sheet1
ID | Category | Task | Start Date | End Date | Dependencies | Skill Needed | Who Did It | Team Member | Strengths / Good Skills | Gaps / Areas to Improve
A1 | Planning | Introduction | 2025-10-01 | 2025-10-03 | None | Project overview, Communication | Mohamed, Erin, Ava, Leyla | Chiko | Problem-solving, Task-efficient | UI/UX design, Project planning
A2 | Planning | Aims & Objectives | 2025-10-04 | 2025-10-07 | A1 | Goal setting, Documentation | Mohamed, Erin, Chiko, Ava | Ava | System design, Team communication | Distractible, Problem-solving
A3 | Research | Literature Review | 2025-10-04 | 2025-10-17 | A1 | Research, Documentation | Erin, Leyla, Mohamed, Ava | Erin | Project planning, Documentation | Problem-solving, Communication
A4 | Analysis | Requirements Analysis | 2025-10-15 | 2025-10-22 | A2 | Requirement gathering, Analysis | Mohamed, Leyla, Ava, Erin | Mohamed | Coding logic, System design | Rushed, Project planning
A5 | Planning | Project Planning | 2025-10-23 | 2025-10-30 | A4 | Scheduling, Timeline, Documentation | Erin, Mohamed, Ava, Leyla | Leyla | UI Design, Team communication | SQL knowledge, Documentation
B1 | UML | Use Case Diagrams | 2025-11-01 | 2025-11-05 | A4 | UML, System Modelling | Leyla, Mohamed, Erin, Ava
B2 | UML | Class Diagrams | 2025-11-06 | 2025-11-10 | A4 | UML, OOP, System Modelling | Leyla, Mohamed, Erin, Ava
B3 | UML | Sequence Diagrams | 2025-11-11 | 2025-11-14 | A4 | UML, Flow Design | Leyla, Mohamed, Erin, Ava
C1 | Risk | Risk Register | 2025-11-15 | 2025-11-22 | A5 | Risk Analysis, Documentation | Erin, Mohamed, Ava, Leyla
D1 | Database | ERD Design | 2025-11-20 | 2025-11-30 | A4 | Database Modelling, SQL | Ava, Erin, Chiko, Leyla
D2 | Database | Test Plan | 2025-11-25 | 2025-12-07 | D1 | Testing, Documentation | Ava, Erin, Mohamed, Leyla
D3 | Database | Normalization | 2025-11-25 | 2025-12-08 | D1 | SQL, Data Optimization | Ava, Erin, Mohamed, Leyla
E1 | UI | UI & Helper Components | 2025-11-01 | 2026-02-28 | None | Tkinter, Python, UI Components | Mohamed, Leyla, Erin, Ava
E2 | UI | Dashboard Template | 2026-03-01 | 2026-03-07 | E1 | UI Design, Layout, Components | Mohamed, Leyla, Erin, Ava
D4 | Database | Database Implementation | 2025-12-15 | 2025-12-21 | D1 | SQL, Table Design, Queries | Ava, Erin, Mohamed, Leyla
F1 | Security | Authentication System | 2025-12-19 | 2025-12-25 | D4 | Security, Login, RBAC | Mohamed, Chiko, Ava, Erin
G1 | Admin | Admin Module – Core | 2026-01-26 | 2026-01-31 | F1 | Backend, CRUD, Role Management | Mohamed, Chiko, Ava, Erin
G2 | Admin | Admin – Finance & Security | 2026-02-01 | 2026-02-06 | G1 | Finance, Security, Reporting | Mohamed, Ava, Chiko, Leyla
H1 | Manager | Manager – Operations | 2026-02-07 | 2026-02-14 | G1 | Operations, Approval, Backend | Chiko, Mohamed, Ava, Erin
H2 | Manager | Manager – Reports | 2026-02-15 | 2026-02-17 | H1 | Analytics, Reporting, SQL | Leyla, Erin, Mohamed, Ava
I1 | Finance | Finance – Transactions | 2026-02-18 | 2026-02-20 | F1/G1 | Payment Processing, Backend | Ava, Chiko, Leyla, Erin
I2 | Finance | Finance – Reports | 2026-02-21 | 2026-02-26 | I1 | Reporting, Billing, SQL | Ava, Erin, Chiko, Leyla
J1 | Maintenance | Maintenance – Requests | 2026-02-27 | 2026-03-01 | H1 | Maintenance Tracking, Logging | Chiko, Mohamed, Leyla, Erin
J2 | Maintenance | Maintenance – Scheduling | 2026-03-02 | 2026-03-07 | J1 | Scheduling, Notifications | Chiko, Mohamed, Ava, Erin
K1 | Front Desk | Front Desk – Registration | 2026-03-08 | 2026-03-09 | F1/E1 | Registration, Data Entry | Leyla, Erin, Mohamed, Ava
K2 | Front Desk | Front Desk – Records | 2026-03-10 | 2026-03-11 | K1 | Record Updates, Logging | Leyla, Erin, Ava, Mohamed
L1 | Tenant | Tenant – Profile | 2026-03-12 | 2026-03-13 | F1 | Profile Management, UI | Mohamed, Chiko, Leyla, Erin
L2 | Tenant | Tenant – Records | 2026-03-14 | 2026-03-15 | L1 | Payment, Maintenance Tracking | Ava, Erin, Mohamed, Leyla
M1 | Security | Security & Validation | 2026-03-16 | 2026-03-19 | D4 | Authentication, SQL, Audit | Mohamed, Chiko, Ava, Erin
M2 | QA | Final Testing | 2026-03-20 | 2026-03-20 | All Modules | Testing, Verification | Mohamed, Ava, Erin, Leyla
N1 | Reporting | Compile Final Report | 2026-03-21 | 2026-03-22 | All Modules | Report Writing | All Students
N2 | Reporting | Individual Reflection & Demo | 2026-03-23 | 2026-03-30 | All Modules | Reflection, Presentation | All Students